## UX research-design Billing Cent
| Phases / timing | Stage | Week | Activity | Detailed Activity Description | Effort (Days Total) | Skills | Effort (Days)2 | Skills (supporting) | Effor Days
Discovery & Research Phase
Stage |  |  | 1 | Project Lead | Design strategy and direction, coordination, stakeholder engagement | 4 | Design Strategy
1 | Week 2nd Dec 2024 | Research Recruitment & Operations | 1 | Research Recruitment & Operations | Recruit users, schedule sessions, and manage operations for testing and research phases. | 3 | Research Ops
1 |  | Discovery & Research Phase | 1 | Conduct current state review | Gather data from internal workshops, and user interviews, surveys, and observations to understand user pain points and expectations around billing. | 1 | UX research | 1 | Maguire input / review | 1
|  | Discovery & Research Phase |  |  | Map out research and design scope across engagements | 1 | UX research | 1
1 |  | Discovery & Research Phase | 1 | Competitive Analysis | Analyse other platforms handling of billing features and identify strengths and gaps from a usability perspective | 1 | UX design | 1
1 |  | Discovery & Research Phase | 2 | Map Customer Journey | Map out the key touchpoints and pain points in the future state billing process to guide design improvements, particularly around CCS guidance, split between live balance and payment due, and pay now nudges and CTAs, as well as notifications | 3 | UX research | 2 | Maguire input / review | 1
1 |  | Discovery & Research Phase | 2 | Create Personas | Develop user personas based on research to guide the design process. | 1 | UX research | 0.5 | UX design | 0.5
Design Phase
|  |  |  | Project Lead | Design strategy and direction, coordination, stakeholder engagement | 14
2 |  | Information Architecture | 3 | Organise Billing Information | Structure billing data (e.g., current, past, and due payments) for organisation and presentation. | 2 | UX research | 1 | UX design | 1
2 |  | Information Architecture | 3 | Card Sorting / Tree Testing | Test the billing structure with users to validate the information architecture (IA). | 2 | UX research | 2 |  | 8-10 users / staff
2 | 2 week BREAK NY | Wireframing Phase | 5 | Create Low-Fidelity Wireframes | Create basic layout and functionality wireframes for the items in scope | 5 | UX design | 5
2 | Week 6th Jan 2025 | Wireframing Phase | 5 | Usability Testing of Wireframes | Test wireframes with users to gather feedback on layout and interaction. | 3 | UX research | 3 |  | 8-10 users / staff
2 |  | Wireframing Phase | 6 | Refine Wireframes | Iterate on wireframes based on usability testing feedback. | 2 | UX design
3 | Mid-fidelity | Research Recruitment & Operations | 6 | Research Recruitment & Operations | Coordinate with users for usability testing and prototype feedback. | 2 | Research Ops
3 |  | Interaction Design Phase | 7 | Design Core Interactions | Design how users interact with buttons, filters, payments, and downloading features. | 5 | UX design
3 |  | Interaction Design Phase | 7 | Prototype design | Create interactive prototypes for testing with users. | 3 | UX design | 1 | Maguire input / review
3 |  | Interaction Design Phase | 8 | Prototype Testing | User research workshops | 4 | UX research |  | 8-10 users/customers
3 |  | Interaction Design Phase | 8 | Refine Interactions | Refine interaction designs based on feedback from prototype testing. | 2 | UX design
4 | High-fidelity | Research Recruitment & Operations | 8 | Research Recruitment & Operations | Recruit users, schedule sessions, and manage operations for interaction testing. | 2 | Research Ops
4 |  | Visual Design Phase | 9 | Apply Branding and Visual Style | Apply branding, colours, fonts, and create a high-fidelity visual design. | 5 | UX design
4 |  | Visual Design Phase | 9 | Ensure Accessibility | Ensure the design meets accessibility standards (e.g., colour contrast, legibility). | 1 | UX design
4 |  | Development Handoff | 10 | Prepare Design Specifications | Prepare detailed design specifications for developers, including assets and styles. | 3 | UX design | 1 | Maguire input / review
4 |  | Research Recruitment & Operations | 11 | Research Recruitment & Operations | Recruit users, schedule sessions, and manage operations for post-launch testing. | 2 | Research Ops
Development Phase
|  |  |  | Project Lead | Design strategy and direction, coordination, stakeholder engagement | 2
| Week 24th Feb 2025 | Development Handoff | 11 | Collaboration with Developers | Collaborate with developers to ensure proper implementation of the design. | 3 | UX design
|  | QA Testing Phase | 11 | QA Testing | Test the design during QA to ensure functionality and usability. | 4 | UX design
|  | QA Testing Phase | 12 | Address QA Issues | Address any issues identified during the QA process. | 2 | UX design
Launch Phase
|  | Post-Launch Testing & Iteration | 13 | Post-Launch User Testing | Gather feedback from users interacting with the live "My Bills" section. | 4 | UX research |  | 8-10 users
|  | Post-Launch Testing & Iteration | 13 | Analyse Usage Data | Analyse task completion rates, errors, and user feedback to identify improvements. | 3 | UX design
| Week 24th March 2025 | Post-Launch Testing & Iteration | 14 | Refine & Iterate | Iterate on the design based on post-launch user feedback and data. | 3 | UX design
EFFORT CALCULATION
| Activities | Roles | Week | Activity | Detailed Activity Description | Effort (Days) | People | Effort (Days)2 | People (supporting) | Notes
|  | Research Ops | 1 to 11 |  | Research ops: Recruit users, schedule sessions, and manage operations for testing and research phases. | 9 | Research Ops
|  | UX Researcher | 1 to 13 |  | UX research: Usability, navigation, UX research, testing and validation | 19 | Lena |  | Robyn
|  | Maguire input / review | 1 to 12 |  | SME input, supporting prioritisation effort | 7 | Maguire input / review
|  | UX Designer | 5 to 15 |  | UX Design - Wireframe to detailed design stage | 43.5 | Gaj? |  | Robyn
|  | Project management @2.5 days/week | 1 to 15 |  | Design strategy and direction, coordination, stakeholder engagement | 20 | Lena
| TOTAL |  |  |  |  | 124 | ALL TEAM

## Features x Skillsets x stage
Stage # | Shipping ETA | Stage | Feature/Section | Activity | Details | Notes | Required Skill Set
1 | Maguire scope included | Discovery | Business requirements | Define Customer Categories & Permissions if enforcing Direct Debit as per scope | Determine 'Standard' and 'Flexible' customers, create user labels, design initial prompts |  | Business Analyst, UX Designer
1 | Maguire scope included | Discovery | Discovery and Initial Research | Language and Label Validation | Validate terms like “Live Balance” and “Payment Due” with users to ensure clarity, create library |  | UX Researcher
1 | Maguire scope included | Discovery | Current State analysis | Analyse detailed customer research data specifically on Billing, identify research questions for further research | Gather insights from analytics and user feedback on current billing/personal info interactions |  | Data Analyst, UX Researcher
1 | Maguire scope included | Discovery | Map Customer Research / Data analysis from existing interviews on CCS pain points | Conduct validation as well as discovery research for targeted problem areas | CCS across full website as well as customer barriers around language and concept, define sections and flows for improved CCS experience |  | UX Researcher
1 | Maguire scope included | Low-Fidelity | Language terminology | Define Messaging for New Features | Establish consistent, user-friendly terms for new features across portal and explainer elements (CCS, Payment Plan), set up language library for users |  | UX Designer, Content Strategist
1 | release TBC | Discovery | Bill Payment Nudges | Identify Optimal CTA Locations | Determine where payment CTAs should be placed throughout the portal (e.g., dashboard, account overview, etc.) | Consider optimal locations for CTAs (dashboard, billing statement, etc.) to ensure high visibility | CX Strategist, UX Designer
1 | release TBC | Discovery | Bill Payment Reminders | Define Reminder Triggers | Define when payment reminders should trigger (e.g., due date approaching, overdue, successful payment) | Use notes on reminder timing and messaging to set effective triggers and phrasing for reminders | CX Strategist, UX Designer
1 | release TBC | Discovery | Payment Reminders on Billing Statements | Determine Statement Reminder Content | Outline nudging content for billing statements (e.g., “Pay Now” buttons, payment due date highlights) | Consider billing statement design elements (highlighted due dates, "Pay Now" buttons) for effective prompts | UX Designer, Content Strategist
| Design - LoFi | [5 empty] | UX Designer
2 | Maguire scope included | Low-Fidelity | Direct Debit and Notifications | Low-Fidelity Wireframes and Concept Testing | Show setup, update, and removal flows; add notifications for expiring payment details |  | UX Designer
2 | Maguire scope included | Low-Fidelity | Credit/Debit Card Validation | Wireframe Initial Concept | Design input validation and inline error messages, link to FAQ section |  | UX Designer
2 | Maguire scope included | Low-Fidelity | Live Balance and Payment Due | Low-Fidelity Concept Testing | Develop basic UI for live vs. statement balance, add tooltips |  | UX Designer
2 | Maguire scope included | Low-Fidelity | Overview Dashboard Enhancement | Dashboard Initial Layout | Add live balance, payment due, recent transactions |  | UX Designer
2 | Maguire scope included | Low-Fidelity | Billing Statement Overhaul | Initial Concept and Wireframe | Simplify layout, add 'Download Statement' button, redesign table structure |  | UX Designer
2 | Maguire scope included | Low-Fidelity | Statement Email Updates | Initial Wireframe and CTA Addition | Update email layout with 'Download' and 'Pay Now' buttons |  | UX Designer, Content Strategist
2 | Maguire scope included | Low-Fidelity | Discounts and Offers in Billing | Define and Integrate Offer Tracing | Update billing to show applied discounts or offers |  | UX Designer, UX Researcher
2 | Maguire scope included | Low-Fidelity | CCS Details on Billing | Define and Structure CCS Info | Include CCS information per child, such as Enrolment ID, eligible hours, and more |  | UX Designer
2 | Maguire scope included | Low-Fidelity | Payment Plan design | Define Payment Plan Display | Show frequency, installment amount, method, and schedule on billing statements |  | UX Designer
2 | Maguire scope included | Low-Fidelity | Billing for New Products | Define Sorting and Filtering for Products | Allow users to sort/view billing by product (e.g., OSHC, Rocketeers) |  | UX Designer, Content Strategist
2 | Maguire scope included | Low-Fidelity | Help Section incl. CCS | Define Content & Layout | Identify FAQ topics, design initial Help Section layout, position Statement Guide & Calculator |  | UX Designer
2 | Maguire scope included | Low-Fidelity | Help Section incl. CCS | Wireframe Interactive Elements | Create basic wireframes for “How to Read Your Statement” guide and CCS Calculator |  | UX Designer
2 | Maguire scope included | Low-Fidelity | Help Section incl. CCS | Determine Access Points | Plan access points for the Help Section from key areas within the Parent Portal |  | UX Designer
2 | Maguire scope included | Low-Fidelity | Payment Reminders on Billing Statements | Statement CTA Layout | Design initial layout for billing statements, including prominent “Pay Now” buttons and due date highlights | Use notes on billing statement elements (due dates, payment status) to enhance CTA visibility | UX Designer
2 | release TBC | Low-Fidelity | Bill Payment Nudges | Initial CTA Wireframe | Design wireframes for “Pay Now” and other payment CTAs on key pages, such as the dashboard and account overview | Apply optimal placement notes in wireframes to ensure CTAs are visible on relevant pages | UX Designer
2 | release TBC | Low-Fidelity | Bill Payment Reminders | Reminder Placement Wireframe | Create wireframes for reminder placements, including pop-ups, banners, and in-line messages | Incorporate reminder timing and visibility cues in wireframe placement (e.g., pop-ups) | UX Designer
2 | Future State Concepts
2 | Future State Concepts | Low-Fidelity | Personalised Payment & Spending Insights | Initial Concept & Wireframe | Design a personalised dashboard summarising past payments, savings, and upcoming expenses |  | UX Designer
2 | Future State Concepts | Low-Fidelity | Incentivised On-Time Payments | Loyalty & Rewards Concept Wireframe | Create initial wireframe for loyalty points or rewards feature for on-time payments |  | UX Designer, CX Strategist
2 | Future State Concepts | Low-Fidelity | Flexible Payment Options | Initial Concept & Wireframe | Design wireframe for instalment options, autopay, and scheduled payment functionality |  | UX Designer, CX Strategist
2 | Future State Concepts | Low-Fidelity | Enhanced Reminders and Notifications | Reminder Settings & Wireframe | Develop wireframe for customisable reminder preferences and in-portal reminders |  | UX Designer, CX Strategist
2 | Future State Concepts | Low-Fidelity | Subscription or Membership Model | Subscription Tier Wireframe | Initial wireframe for subscription or membership tiers with exclusive benefits |  | UX Designer, Business Analyst
2 | Future State Concepts | Low-Fidelity | Bundled Services & Packages | Initial Concept Wireframe | Create wireframe for bundle and package offers, providing cost savings for bundled service purchases |  | UX Designer, CX Strategist
2 | Future State Concepts | Low-Fidelity | Upsell and Cross-Sell Opportunities | Targeted Recommendations Wireframe | Design targeted recommendations feature for complementary services based on usage patterns |  | UX Designer, Data Analyst
2 | Future State Concepts | Low-Fidelity | Interactive and Supportive Tools | Savings Calculator Concept Wireframe | Develop wireframe for an in-portal savings calculator for CCS and other service packages |  | UX Designer
2 | Future State Concepts | Low-Fidelity | Real-Time Financial Assistance Options | Payment Extension Concept Wireframe | Design initial concept for short-term payment extensions for eligible users |  | UX Designer, CX Strategist
2 | User testing
2 | Design mid-fi
3 | Maguire scope included | Mid-Fidelity | Direct Debit and Notifications | Mid-Fidelity Wireframe Iterations | Refine flows, add prompts, update designs based on user feedback |  | UX Designer
3 | Maguire scope included | Mid-Fidelity | Credit/Debit Card Validation | User Testing & Mid-Fidelity Adjustments | Test card input flow with users, refine error guidance |  | UX Researcher, UX Designer
3 | Maguire scope included | Mid-Fidelity | Live Balance and Payment Due | Mid-Fidelity Wireframe Refinement | Refine based on user testing, add color coding or icons |  | UX Designer
3 | Maguire scope included | Mid-Fidelity | Overview Dashboard Enhancement | Testing and Mid-Fidelity Refinement | Organise dashboard for clarity, test with users |  | UX Designer
3 | Maguire scope included | Mid-Fidelity | Billing Statement Overhaul | Mid-Fidelity Adjustments | Adjust for clarity based on feedback, apply UI consistency |  | UX Designer
3 | Maguire scope included | Mid-Fidelity | Statement Email Updates | Testing and Refinement | Test readability and usability on desktop/mobile |  | UX Designer, UX Researcher
3 | Maguire scope included | Mid-Fidelity | Discounts and Offers in Billing | Wireframe and User Testing | Add discounts section to billing statement, test for clarity |  | UX Designer, UX Researcher
3 | Maguire scope included | Mid-Fidelity | CCS Details on Billing | Wireframe and Testing for Clarity | Redesign billing section to organise CCS info effectively |  | UX Designer, CX Strategist
3 | Maguire scope included | Mid-Fidelity | Payment Plan design | Design and Testing | Structure payment plan section to clarify past/future installments |  | UX Designer, CX Strategist
3 | Maguire scope included | Mid-Fidelity | Billing for New Products | Design for Billing Section and Dashboard | Update billing to display products used by child, enable sorting by product type |  | UX Designer, CX Strategist
3 | Maguire scope included | Mid-Fidelity | Help Section incl. CCS | Prototype Help Section | Develop mid-fidelity wireframes, organise FAQs by topic, refine search/navigation |  | UX Designer, Content Strategist
3 | Maguire scope included | Mid-Fidelity | Help Section incl. CCS | Enhance Interactive Elements | Refine layout for Statement Guide and CCS Calculator; add tooltips and clear labels |  | UX Designer
3 | Maguire scope included | Mid-Fidelity | Help Section incl. CCS | User Testing & Adjustments | Conduct testing to validate usability; adjust FAQ content and interactive tool functionality |  | UX Researcher, UX Designer
3 | release TBC | Mid-Fidelity | Bill Payment Nudges | Prototype & User Testing for CTAs | Refine CTA placements and run user testing to ensure visibility and ease of use | Adjust CTA placements based on user feedback and optimal location notes | UX Designer, UX Researcher
3 | release TBC | Mid-Fidelity | Bill Payment Reminders | Reminder Message Refinement | Test and refine reminder messages for effectiveness, including language and timing of nudges | Refine based on reminder messaging notes for clarity and impact | UX Designer, Content Strategist
3 | Maguire scope included | Mid-Fidelity | Payment Reminders on Billing Statements | Prototype Billing Statement CTAs | Refine the billing statement layout for clarity, optimising “Pay Now” buttons and payment prompts | Incorporate feedback from testing; adjust according to billing statement layout notes | UX Designer, UX Researcher
3 | Future State Concepts | Mid-Fidelity | Personalised Payment & Spending Insights | Prototype & User Testing | Refine personalised insights; test with users to ensure clarity and usefulness |  | UX Designer, UX Researcher
3 | Future State Concepts | Mid-Fidelity | Incentivised On-Time Payments | Loyalty Prototype & Testing | Refine wireframe with user feedback, ensuring reward clarity and motivation |  | UX Designer, UX Researcher
3 | Future State Concepts | Mid-Fidelity | Flexible Payment Options | Prototype & User Testing | Refine instalment and autopay options based on user feedback |  | UX Designer, UX Researcher
3 | Future State Concepts | Mid-Fidelity | Enhanced Reminders and Notifications | Prototype & User Testing | Test user preference settings and reminder visibility; refine based on feedback |  | UX Designer, UX Researcher
3 | Future State Concepts | Mid-Fidelity | Subscription or Membership Model | Prototype Subscription Tiers & Benefits | Refine subscription offerings and benefits; test appeal and clarity with users |  | UX Designer, Business Analyst
3 | Future State Concepts | Mid-Fidelity | Bundled Services & Packages | Prototype Package Offers & Testing | Refine bundle offers for clarity and perceived value; test package options with users |  | UX Designer, UX Researcher
3 | Future State Concepts | Mid-Fidelity | Upsell and Cross-Sell Opportunities | Prototype & User Testing | Refine targeted recommendations; test recommendations with users for relevance |  | UX Designer, UX Researcher
3 | Future State Concepts | Mid-Fidelity | Interactive and Supportive Tools | Prototype Savings Calculator | Refine savings calculator based on user feedback; ensure clarity and ease of use |  | UX Designer, UX Researcher
3 | Future State Concepts | Mid-Fidelity | Real-Time Financial Assistance Options | Prototype Payment Extension Option | Refine payment extension interface and messaging; ensure clarity and accessibility |  | UX Designer, UX Researcher
3 | User testing
3 | Design hi-fi | [5 empty] | Required Skill Set
4 | Maguire scope included | High-Fidelity | Direct Debit and Notifications | High-Fidelity Prototyping | Finalise prompts, tooltips, and visual indicators for restrictions based on category |  | UX Designer
4 | Maguire scope included | High-Fidelity | Credit/Debit Card Validation | High-Fidelity Finalisation | Add finalised error feedback, expiration alerts, accessible design |  | UX Designer
4 | Maguire scope included | High-Fidelity | Live Balance and Payment Due | High-Fidelity Prototype and Testing | Finalise visual elements, tooltips, and color coding |  | UX Designer
4 | Maguire scope included | High-Fidelity | Overview Dashboard Enhancement | High-Fidelity Finalisation | Apply visual polish, finalise for development |  | UX Designer
4 | Maguire scope included | High-Fidelity | Billing Statement Overhaul | High-Fidelity Finalisation | Finalise new layout, ensure mobile compatibility |  | UX Designer
4 | Maguire scope included | High-Fidelity | Statement Email Updates | High-Fidelity Finalisation | Finalise buttons, improve links, add next direct debit info |  | UX Designer
4 | Maguire scope included | High-Fidelity | CCS Details on Billing | Statement of Entitlement Redesign | Separate CCS details into a distinct format for easy viewing |  | UX Designer
4 | Maguire scope included | High-Fidelity | Billing for New Products | Dashboard & Account Enhancements for Shared Accounts | Consider shared accounts, linked children, and varied products for billing |  | UX Designer, Data Analyst
4 | Maguire scope included | High-Fidelity | Help Section incl. CCS | Finalise Help Section UI | Complete detailed design for FAQ layout, collapsible sections, and search functionality |  | UX Designer, Content Strategist
4 | Maguire scope included | High-Fidelity | Interactive Guides | Polish Interactive Guides | Finalise tooltips, add step-by-step tour for Statement Guide, complete CCS Calculator UI |  | UX Designer, Content Strategist
4 | Maguire scope included | High-Fidelity | Help Section | Accessibility & Final Testing | Ensure accessibility of all elements; conduct final testing for usability and functionality |  | UX Designer, Accessibility Specialist
4 | release TBC | High-Fidelity | Bill Payment Nudges | Finalise CTA Design & Implementation | Complete high-fidelity design of payment CTAs and integrate them across relevant pages on the portal | Finalise CTA locations as per visibility and effectiveness notes for seamless integration | UX Designer
4 | release TBC | High-Fidelity | Bill Payment Reminders | Finalise Reminder Designs & Testing | Finalise designs for reminders, including banners, pop-ups, and in-line messages; test final functionality | Confirm reminder timing and messaging meet project goals based on initial notes | UX Designer, UX Researcher
4 | release TBC | High-Fidelity | Payment Reminders on Billing Statements | Finalise Billing Statement Reminders | Finalise high-fidelity billing statement with clear payment prompts, due date highlights, and “Pay Now” CTAs | Ensure billing statement aligns with additional notes on highlighting due dates, payment status, and CTAs | UX Designer
4 | release TBC | High-Fidelity | Payment Reminder Frequency & Customisation | Allow Users to Customise Reminder Settings | Design a settings page where users can adjust frequency and type of payment reminders (email, SMS, in-portal) | Consider user preferences for reminders; provide flexibility in reminder settings for customisation | UX Designer, Business Analyst
4 | release TBC | High-Fidelity | Testing for All Payment Nudges & Reminders | End-to-End Testing of Payment Features | Conduct end-to-end testing to ensure all payment nudges, CTAs, and reminders work seamlessly and effectively | Verify all reminders, CTAs, and nudges are well-integrated for maximum usability and impact | UX Researcher, QA Specialist
4 | Future State Concepts | High-Fidelity | Personalised Payment & Spending Insights | Finalise Dashboard Design | Finalise the personalised dashboard for seamless integration |  | UX Designer, Data Analyst
4 | Future State Concepts | High-Fidelity | Incentivised On-Time Payments | Finalise Loyalty Rewards UI | Complete design for loyalty or rewards system and integrate for final testing |  | UX Designer, UX Researcher
4 | Future State Concepts | High-Fidelity | Flexible Payment Options | Finalise Payment Flexibility Features | Finalise design for instalments, autopay, and scheduling for final integration |  | UX Designer, Business Analyst
4 | Future State Concepts | High-Fidelity | Enhanced Reminders and Notifications | Finalise Reminder Features | Finalise customisable reminder settings and in-portal reminders for full integration |  | UX Designer, UX Researcher
4 | Future State Concepts | High-Fidelity | Subscription or Membership Model | Finalise Subscription Design | Finalise high-fidelity design for subscription or membership model; prepare for implementation |  | UX Designer, Business Analyst
4 | Future State Concepts | High-Fidelity | Bundled Services & Packages | Finalise Bundle & Package UI | Finalise package design for clear, attractive presentation; prepare for rollout |  | UX Designer
4 | Future State Concepts | High-Fidelity | Upsell and Cross-Sell Opportunities | Finalise Recommendations Feature | Finalise targeted recommendations feature for relevant suggestions to users |  | UX Designer, Data Analyst
4 | Future State Concepts | High-Fidelity | Interactive and Supportive Tools | Finalise Savings Calculator Design | Complete final design for savings calculator with clear, easy-to-use interface |  | UX Designer, UX Researcher
4 | Future State Concepts | High-Fidelity | Real-Time Financial Assistance Options | Finalise Payment Extension Feature | Finalise design for payment extensions; ensure messaging is clear and supportive |  | UX Designer, Business Analyst

## Additional features definitions
Nudges and Reminders: Gentle prompts or notifications within the portal that encourage users to complete tasks, such as paying bills. These can include “Pay Now” CTAs, due date alerts, or overdue reminders, designed to keep users engaged and on track.
Help Section (Including FAQ): A dedicated resource area within the portal providing answers to common questions and guidance on using features like billing, payment, and account management. The FAQ section offers clear, structured answers to frequently asked questions, helping users navigate the portal more effectively.
Future State Features
1. Personalised Payment and Spending Insights
-Overview of Past Payments and Savings: Offer a personalised dashboard that summarises past payments, any applicable savings (from discounts or subsidies), and a forecast of upcoming expenses. This can make users feel more informed and in control, encouraging timely payments.
-Spending Breakdown and Value-Added Insights: Provide a detailed breakdown of their spending by product (e.g., OSHC, Rocketeers) and highlight benefits or “savings realised” from any discounts, which can encourage repeat engagement and additional purchases.
2. Incentivised On-Time Payments
-Loyalty Points or Rewards: Introduce a loyalty program where users earn points for timely payments. Accumulated points could be redeemable for future services, discounts, or exclusive products.
-Discount for Early Payment: Offer a small percentage discount for paying bills early, which not only increases on-time payments but also rewards proactive engagement.
3. Flexible Payment Options
-Payment Plans and Installment Options: Allow customers to pay larger bills in smaller installments, particularly useful for new or higher-value services. Offering options like bi-weekly or monthly installments could make payments more manageable and encourage users to opt for higher-cost services.
-Autopay and Scheduled Payments: Provide an easy, one-time setup for autopay and scheduled payments, reducing the likelihood of missed payments.
4. Enhanced Reminders and Notifications
-Customisable Reminder Preferences: Allow users to set their own reminder frequency and channels (e.g., SMS, email, in-app). This could lead to fewer missed payments since users can select the most effective reminder style for them.
-Contextual Reminders Linked to Portal Activities: If users frequently log in to the Parent Portal, add subtle reminders within high-traffic areas (e.g., dashboard or product pages) that encourage payment completion.
5. Subscription or Membership Model
-Subscription Services for Added Benefits: Consider offering subscription tiers where users get access to additional features or content (e.g., exclusive classes, priority booking) with regular billing. This model encourages ongoing payments and builds customer loyalty.
-Bundled Services: Create package deals or bundle products that provide savings or extra benefits when purchased together (e.g., OSHC and Rocketeers packages), which can increase overall spending per user.
6. Upsell and Cross-Sell Opportunities
-Targeted Recommendations: Use spending patterns to suggest related or complementary services. For example, if a user frequently books after-school care, suggest holiday programs or educational workshops with an exclusive “add-on” discount for members.
-Personalised Offers: Tailor offers based on past usage patterns. For example, provide discounts on booking extended care services if they’ve used the same in the past.
7. Interactive and Supportive Tools
-Savings Calculator: Offer a tool where users can input estimated usage to see potential savings with different packages or membership tiers.
-Live Chat and In-App Support: Provide easy access to live chat or customer support within the payment and billing sections, so users can ask questions or resolve issues quickly, reducing payment friction.
8. Real-Time Financial Assistance Options
-Flexible Payment Extensions for Eligible Users: If a user might miss a payment, consider offering a short grace period or flexible extension option within the portal. Providing such support in a timely, automated manner can prevent interruptions and show empathy for customers’ financial needs.
9. Promotions for Adding Additional Family Members or Friends
-Referral Discounts: Offer incentives for users to refer friends or family, such as discounted rates for each new referral who signs up for a paid service.
-Family Bundle Discounts: Create a discount structure where users can add siblings or additional family members to services (e.g., OSHC) at reduced rates, encouraging higher engagement from existing families.

## Critical Path short
| Phase | Action | Dependency | Approval
1 | Discovery & Research | Identify business requirements | Business Teams | CX Lead
2 | Discovery & Research | Align features with CX insights and IT feasibility | CX and IT | CX Lead
3 | Discovery & Research | Finalise requirements | Customer Growth review | Customer Growth
4 | Discovery & Research | Conduct high-level user research | Requirement approval | CX
5 | Design | Create initial design concepts | Approved requirements | CX Lead
6 | Design | Review designs for technical feasibility | IT feedback | IT Lead
7 | Design | Finalise designs | Customer Growth alignment | Customer Growth
8 | Design | Conduct detailed user research | Initial designs completion | CX
9 | Development | Begin technical build | Approved final designs | IT
10 | Development | Provide functional input | Business Team feedback | IT Lead
11 | Development | Review development progress | Customer Growth alignment | Customer Growth
12 | Testing & Validation | Conduct user testing | CX design completion | CX
13 | Testing & Validation | System testing | Post-build completion | IT
14 | Testing & Validation | Verify operational functionality | Business Teams input | CX Lead
15 | Deployment | Oversee technical rollout | IT manages | CX supports
16 | Deployment | Prepare onboarding materials | CX aligns with Business Teams | Customer Growth
17 | Deployment | Final sign-off for launch | Consistency with strategic goals | Customer Growth

## Critical Path
Stage | Action | Description | Dependency | Resources Required | RACI | Additional Notes
Requirements Definition | Define Focus across customer groups | Business teams identify operational needs and collaborate with CX to refine into user-centric features | CX ensures alignment with experience goals; IT assesses feasibility | PM | R: Business Analysts, CX Strategists; A: Customer Growth Representatives; C: IT Solution Architects I: Business Teams, IT Development Team | Stakeholder alignment checkpoints recommended
Requirements Definition | Risk Management Plan | Identify and assess potential project risks | Regular updates at each phase | PM | R: Project Manager; A: Project Sponsor; C: IT; I: Business Teams | Mitigate risks proactively to prevent delays
Research, Design, and Prototyping | Conduct User Research | CX conducts research to gather insights on needs and behaviours | Research informs high-level and detailed designs | User Researcher, UX Designers, CX Strategists, Customer Growth Representatives | R: User Researcher; A: Customer Growth Representatives; C: Business Teams, IT Solution Architects; I: IT Development Team | Research helps refine design choices; documented in each phase
Research, Design, and Prototyping | Create High-Level and Detailed Designs | CX creates and iterates design concepts | IT reviews designs for technical feasibility | UX Designers, CX Strategists, IT Solution Architects, Customer Growth Representatives | R: UX Designers; A: Customer Growth Representatives; C: Business Teams, IT Solution Architects; I: Customer Support | Ensures designs are customer-centric and feasible
Development and Integration | Technical Build and Feature Integration | IT manages the technical build, coordinating with CX to meet UX requirements | Ongoing functional input from Business Teams | Frontend & Backend Developers, CX Designers, IT Project Managers, Business Teams, Customer Growth Representatives | R: IT Development Team; A: IT Project Managers; C: CX Designers, Business Teams; I: Customer Growth Representatives, QA Team | Continuous alignment with Customer Growth goals
Development and Integration | Change Control Process | Evaluate, approve, or reject any scope changes | Regular reviews with key stakeholders | Project Manager, CX Strategists, IT Solution Architects | R: Project Manager; A: Project Sponsor; C: CX Strategists, IT Solution Architects; I: Business Teams | Prevents scope creep, controls budget and timeline
Testing and Validation | User and System Testing | CX conducts user testing; IT performs system testing | Verified functionality from Business Teams | UX Researchers, QA Testers, CX Designers, IT Developers, Business Teams, Customer Growth Representatives | R: UX Researchers, QA Testers; A: Customer Growth Representatives; C: CX Designers, IT Developers, Business Teams; I: Customer Support, IT Project Managers | Ensures quality and usability meet expectations
Deployment and Launch | Finalise Deployment with Customer-Facing Support | IT oversees deployment; CX supports with onboarding materials | All changes aligned with Customer Growth | IT Operations Team, CX Content Specialists, Business Team Leads, Customer Support, Customer Growth Representatives | R: IT Operations Team, CX Content Specialists; A: Customer Growth Representatives; C: Business Team Leads, Customer Support; I: All Internal Teams, End Users | Customer Growth provides final sign-off on launch
Post-Launch Monitoring | Monitor KPIs and Gather User Feedback | Track performance metrics, user feedback, and technical performance post-launch | Immediate feedback from deployment | Customer Support, CX Researchers, IT Support, Business Analysts | R: Customer Support; A: Customer Growth Representatives; C: CX Researchers, IT Support, Business Analysts; I: Business Teams, IT Development Team | Enable data-driven improvements for future phases
Documentation and Knowledge Transfer | Capture Key Insights and Design Choices | Document design choices, research insights, and technical architecture | Ongoing documentation in each phase | Project Manager, CX Designers, IT Solution Architects, Customer Growth Representatives | R: Project Manager; A: Customer Growth Representatives; C: CX Designers, IT Solution Architects; I: All Project Stakeholders | Supports continuity, onboarding, and future maintenance

## IT requirements
Parent Portal features summary
Features | Type | Project | Proposed Details | KPIs | Technical feasibility (IT to comment, please include likely delivery date) | Effort (IT to comment to help gauge how complex this is, informing prioritisation) | Dependency (IT to comment to help inform prioritisation and sequencing of research and design work preceeding the build) | Limitations, concerns, comments, questions | Test methods | Priority
General Help Section | Core Module | Maguire, Day One Onboarding, Moonracer CX | • Purpose: Provide parents with a centralised hub for all onboarding and support resources. • Features: • Searchable Knowledge Base: Allow users to search for answers across general FAQs and billing help. • General FAQ Content: Include topics such as bookings, cancellations, session updates, and child support services. • Clear Navigation: Organise FAQs into categories like “Getting Started,” “Bookings,” and “Payments.” • CTA for Additional Support: Include a clear link to contact the dedicated support team for unresolved issues (e.g., “Still need help? Contact our team here.”). Technical Requirements • Search and Routing: • Implement a robust search function for the knowledge base and billing FAQs. • Ensure persona routing logic is clear and intuitive. • CMS Integration: • Enable the business team to update FAQs and persona-based pages as needed. • Responsive Design: • Ensure all features are optimised for mobile and desktop use. • Analytics and Reporting: • Track user interactions (e.g., search queries, FAQ views, and contact clicks) to identify common pain points. | Customer satisfaction (%+ helpfulness rating). | Feasible; a lot of different features here | Large | cannot answer at this stage |  | Prototype and test with users | Low
New customer section within the Parent Portal with a modular design for easy expansion. | Core Module | Maguire, Day One Onboarding, | • Purpose: easier onboarding reducing contact centre calls and building customer loyalty • Ensure it includes: • FAQs tailored for new customers. • Payment setup instructions and links. • Policies and onboarding resources (e.g., cancellation rules, booking guides). • Enable content updates via the CMS to keep the section current and relevant. • Optimise the section for mobile and desktop, ensuring smooth navigation and quick load times. | New customer onboarding completion rate (%). | Feasible; a lot of different features here | Large |  |  | Additional research is needed. I recommend using the following research methods: card sorting and one-on-one interviews to identify user stories, followed by either high-detail wireframes or low-detail prototypes. | Medium | Email
Dashboard module / landing page in parent portal | Core Module | Maguire, Day One Onboarding, Moonracer CX | Develop a dashboard module that includes: • Real-time billing status updates (e.g., “Payment Processed,” “Payment Failed—Action Needed”). • Links to actions such as retrying failed payments or updating payment details. • A banner for incomplete setups (e.g., “Your payment method isn’t set up yet. Click here to complete.”). • Ensure the dashboard integrates seamlessly with existing systems, pulling data from payment processing and account status APIs. • Optimise the design for mobile and desktop platforms, with fast load times and responsive functionality. | Retention rate (% repeat usage). | Is this to be done by the Maguire project or not? |  |  |  | Prototype is already complete. I will share it with you. However, it may need updates based on new findings since I designed this in early 2023. | Medium | People
"My Settings” section within the Parent Portal | Core Module | Maguire, Day One Onboarding, Moonracer CX | Develop a “My Settings” section within the Parent Portal to allow users to adjust notifications and manage billing preferences. The section should include the following functionality: •Communications Preferences: •opt in/out of emails and sms (as part of Communication Preferences): Notification Preferences: • Enable users to toggle on/off specific types of notifications (e.g., booking reminders, payment alerts, service updates). • Provide clear categories for notifications (e.g., General Updates, Billing Alerts, Child Activity Highlights). • Include real-time save confirmation after changes. • Billing Preferences: • Allow users to update payment methods (e.g., switching between bank transfer and credit card). • Include an option to adjust payment dates within allowed flexibility. • Display the current billing setup and provide actionable links for changes (e.g., “Update Card Details”). • Security and Accessibility: • Include secure authentication to protect sensitive billing information - 2FA/MFA in billing interactions • Ensure the section is responsive and user-friendly on both desktop and mobile devices. • Integration and Updates: • Connect seamlessly with the backend payment and notification systems to ensure changes are reflected in real time. • Log user changes for troubleshooting and compliance purposes. • Banner or Help Option: • Add a help section or FAQ link for users who need guidance on notification or billing adjustments. |  | Feasible; a lot of different features here | Large |  |  | Further research is needed to determine the types, categories, and delivery methods of notifications. After that, a prototype can be designed. We also need to consider the notification portal(create notifications) for internal users. | Medium
Seamless Registration process | Registration | Onboarding | Account creation, User creation and child enrolment | [5 empty] | The prototype is halfway completed. More research is needed to identify any new pain points. | High
Notifications
Notifications | Notifications: new customer | Maguire, Day One Onboarding, Moonracer CX | Notifications: • Confirmation of enrolment and instructions for booking • Instructions on how to access the Welcome Pack. | Timely engagement (% opened or acted upon). | Feasible | Medium |  |  |  | High | Notifications
Notifications | Notifications: new customer | Maguire, Day One Onboarding, Moonracer CX | Notifications: • Booking confirmation • Reminder to check the Welcome Pack for first-day tips and key information. | Timely engagement (% opened or acted upon). | Feasible | Medium |  |  |  | High
Notifications | Notifications: all customers | Maguire, Day One Onboarding, Moonracer CX | Notifications: • Reminder to book • Links to info on subsidies [part of Billing FAQs/support.] | Timely engagement (% opened or acted upon). | Feasible | Medium |  |  |  | High | Notifications
Notifications | Notifications: all customers | Maguire, Day One Onboarding, Moonracer CX | Notifications: • Reminder to book • CTA to reach out to dedicated contact center team if any questions | Timely engagement (% opened or acted upon). | Feasible | Medium |  |  |  | High | Notifications
Notifications | Notifications: new customers | Maguire, Day One Onboarding, Moonracer CX | Notifications: Reminders about upcoming first payments and links to billing FAQs/support. | Timely engagement (% opened or acted upon). | Feasible | Medium |  |  |  | High | Maguire
Notifications | Notifications: new customers | Maguire, Day One Onboarding, Moonracer CX | Notifications: • Survey notification: “We’d love to hear about your first week!” • Upcoming events or activity previews for continued engagement. | Timely engagement (% opened or acted upon). | Feasible | Medium |  |  |  | High | Notifications
Notifications | Notifications: new customers | Maguire, Day One Onboarding, Moonracer CX | Notifications: “Your first OSHC payment of $XX is due tomorrow. Let us know if you have any questions!” Your Child Care Subsidy for this week has NOT yet been applied. Your fee is... OR: your Child Care Subsidy has been successfully applied, lowering your fee to $XX | Timely engagement (% opened or acted upon). | Feasible | Medium |  |  |  | High | Maguire
Notifications | Notifications: all customers | Maguire, Day One Onboarding, Moonracer CX | Notifications: Missed Payment Follow-Ups: • Friendly reminders for overdue payments, escalating over time. • Example: “Your payment is overdue by 3 days. Avoid disruptions by paying now—click “Your payment for [Date] is overdue. Please process by [Date] to avoid disruptions!” payment has failed again - arrange payment by xxx, then you move into exclusion | Timely engagement (% opened or acted upon). | Feasible | Medium |  |  |  | High | Maguire
Notifications | Notifications: all customers | Maguire, Day One Onboarding, Moonracer CX | Notifications: Bounced Payments: • Immediate notifications via SMS/email: “Your payment didn’t go through. Let’s resolve this quickly—click here.” | Timely engagement (% opened or acted upon). | Feasible | Medium |  |  |  | High | Maguire
Notifications | Notifications: all customers | Maguire, Day One Onboarding, Moonracer CX | Notifications: “A reminder that your next bill for CA will be due in xxx. Your last spend was: $XX” | Timely engagement (% opened or acted upon). | Feasible | Medium |  |  |  | High | Maguire
Billing - Portal features to facilitate on-time payment and self-serve issue resolution
Direct debit form, reinforced with guided input and error message | Billing Features | Maguire |  | Error resolution rate (% successful submissions). |  |  |  |  | Prototype | High | Maguire
Time-activated pop-up that triggers after a user spends a specific amount of time on the payment options or related pages. | Billing Features | Maguire | • Ensure the pop-up is non-intrusive, easy to close, and compatible with mobile and desktop browsers. • Configure tracking to measure the effectiveness of the pop-up in driving payment sign-ups. • Provide CMS integration for updating pop-up content as needed. Text: “Unsure about sharing your payment details? Learn how we support families with our convenient and secure payment options…” | Engagement rate (% clicks on CTAs). | Feasible | Large |  |  |  |  | Maguire
Payment history section highlights missed or overdue payments + CTA | Billing Features | Maguire | • within section: CTA: “Set up a payment plan to avoid future late fees.” | Overdue payment resolution rate (% cleared via CTAs). | Feasible | Large |  |  | Prototype or High level wireframe | High | Maguire
Contact Centre Integration: Direct Contact Link via button | Support Features | Maguire, Moonracer CX | Contact Centre Integration: Direct Contact Link via button • Purpose: Provide seamless access to the dedicated contact centre team for escalated issues. • Features: • Direct Contact Link: Prominently display a button linking to the contact form or chat support (e.g., “Contact Our Support Team”). | Resolution speed (time to resolution). | Feasible | Large |  |  | No prototype or wireframe needed | Low | Maguire
Contextual Routing: Automatically pre-fill contact forms with the user’s current query or FAQ topic for faster resolution. | Billing Features | Maguire, Moonracer CX | Contextual Routing: Automatically pre-fill contact forms with the user’s current query or FAQ topic for faster resolution. | Query resolution accuracy (% resolved without escalation). | Feasible | X-Large |  |  | No prototype or wireframe needed | Low | Maguire
Phone and Email Support Details | Support Features | Maguire, Moonracer CX | • Phone and Email Support Details: Include alternative contact options for urgent assistance. | Contact usability rating (% positive feedback). |  |  |  |  | Prototype | Low | Maguire
De﻿dicated Support Pathways across the site | Support Features | Maguire | Provide links to customer care | Escalation reduction rate (% resolved without escalation). |  |  |  |  | Prototype | Low | Maguire
Banner in Parent Portal | Informational Elements | Maguire | Banner in Parent Portal Bounced Payments: e.g.: Portal Alert: Visible banner prompting action: “Update your payment method or contact us for assistance.” | Click-through rate (% CTA engagement). | Feasible | Large |  |  | Prototype | Medium | Maguire
Persona-Based Help Pages (Routed from Billing FAQ) | Billing Features | Maguire | • Purpose: Offer tailored solutions based on specific user needs or concerns. • Routing Logic: Include a question like, “What best describes your situation?” with options leading to relevant pages: • Option 1: I need flexibility with my payments. • Page Content: Solutions for casual workers, shift workers, or families needing adaptable options. • Links to manage payment schedules or align payments with income. • Option 2: I want to stay in control of my payments. • Page Content: Details about reviewing invoices, updating payment methods, and receiving notifications. • Links to set up alerts or make changes. • Option 3: I share financial responsibilities with someone else. • Page Content: Guidance for co-parents or families managing joint accounts. • Links to set up shared notifications or preferences. • Build a dynamic FAQ page that supports persona-based segmentation, allowing users to navigate content relevant to their concerns (e.g., flexible payment needs, security, shared accounts). • Ensure fast loading, mobile responsiveness, and accessibility compliance (WCAG). • Integrate links to the sign-up page with smooth transitions between FAQ and payment setup. • Implement content management system (CMS) functionality for easy updates to FAQ content. | Call deflection rate (% reduction in billing-related queries). | Feasible; a lot of different features here | Large |  |  | Further research is needed to determine the possible routes. Prototype | Low
Billing FAQ/Help Section within the General Help Section | Billing Features | Maguire, Day One Onboarding, Moonracer CX | • Purpose: Address all billing-related concerns, including payment processes, policies, and potential issues. • Features: • Overview of Billing System: Highlight key information about the retrospective payment system (e.g., invoices sent weekly after service usage, direct debit setup). • Interactive FAQ Content: Include detailed explanations of common topics like late fees, payment schedules, and missed payments. • Quick Links to Key Actions: Provide links to update payment details, retry failed payments, or review invoices. • CTA to Persona-Based Help Pages: Direct users to pages addressing specific concerns (e.g., casual workers, shared accounts). | Direct debit conversion rate (% completed sign-ups). | Feasible; a lot of different features here | Large |  |  | Additional research is required to identify the frequently asked questions (FAQs). Prototype | Low
Maguire
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Cannot provide delivery date until the scope and size of work is known and this feature is prioritized by ExCo Reply: Agree and understand, the purpose of this question is to help us all prioritise and understand trade-offs at a high level, as proposed to be discussed in a follow-up working session. Is there a better way to ask this question to help us do this? @Julieanne Mortimer
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Lena Belin can we please also include a contact us form with drop downs so that customers can easily select what their query relates to. Billing, Booking, CCS, Other (we can get CSC input for which categories would be best) Reply: @Robyn Simper agree - I have this under the billing section (line 22 onwards) but in my mind this should be everywhere including at the higher hierarchy level (Billing FAQs would be part of this general help section). Do you think we need should consolidate and move the whole support experience up here in one block instead?
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Lena Belin this preference centre should also include ability to opt in/out of emails and sms Reply: Also add 2FA/MFA when updating payment details Reply: Done, thank you @Robyn Simper
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Lena Belin what is the welcome pack? Reply: That is the ‘flipbook’ - the one resource that has it all - [or the Families section on the website plus cheat sheet that we talked about yesterday] @Robyn Simper
Note on D28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Lena Belin we should include online chat here Reply: @Robyn Simper Thank you, agree that chat would be the best option for on the spot support, but I’m not sure we have a clear value proposition for investing into this right now. Do you think we should prioritise this as a feature? If so, we’d need to map the value of this over other features, and investment and speak to Wes’ team about feasibility before putting it in. Definitely can do that, but would just require more work before we put it in. What do you think?

## Project Plan Q3
Feature | Due / Priority | Description | Activities
Direct debit nudge | 28th Feb | Benefits page on our approach to billing | detailed design | validate designs w customers
Direct debit nudge | 28th Feb | Direct debit form, reinforced with guided input and error message | detailed design | validate designs w customers
Direct debit nudge | 28th Feb | Time-activated pop-up that triggers after a user spends a specific amount of time on the payment options or related pages, linking to FAQ section | detailed design | validate designs w customers
My statements' section |  | Interface design: Create the user interface for the My statements section, covering transaction details, payment history, and status. Payment history section highlights missed or overdue payments + CTA | detailed design | validate designs w customers
Payment nudges | 28th Feb | Banner in Parent Portal: Bounced Payments: e.g.: Portal Alert: Visible banner prompting action: “Update your payment method or contact us for assistance.” | detailed design | validate designs w customers
maguire help section/FAQ | 28th Feb | Purpose: Provide parents with a centralised hub for all onboarding and support resources. Features: Searchable Knowledge Base: Allow users to search for answers across general FAQs and billing help. General FAQ Content: Include topics such as bookings, cancellations, session updates, and child support services. Clear Navigation: Organise FAQs into categories like “Getting Started,” “Bookings,” and “Payments.” CTA for Additional Support: Include a clear link to contact the dedicated support team for unresolved issues (e.g., “Still need help? Contact our team here.”). Technical Requirements Search and Routing: Implement a robust search function for the knowledge base and billing FAQs. Ensure persona routing logic is clear and intuitive. CMS Integration: Enable the business team to update FAQs and persona-based pages as needed. Responsive Design: Ensure all features are optimised for mobile and desktop use. Analytics and Reporting: Track user interactions (e.g., search queries, FAQ views, and contact clicks) to identify common pain points. | create high-level design concept | prepare for testing / iterate | validate designs w customers | detailed design | prepare for testing / iterate | validate designs w customers
maguire statement design | 28th Feb |  | review existing designs | prepare for testing / iterate | validate designs w customers
dashboard | 28th Feb | Develop a dashboard module that includes: Real-time billing status updates (e.g., “Payment Processed,” “Payment Failed—Action Needed”). Links to actions such as retrying failed payments or updating payment details. A banner for incomplete setups (e.g., “Your payment method isn’t set up yet. Click here to complete.”). Ensure the dashboard integrates seamlessly with existing systems, pulling data from payment processing and account status APIs. Optimise the design for mobile and desktop platforms, with fast load times and responsive functionality. | review existing designs | prepare for testing / iterate | validate designs w customers
FAQ/Help section | 28th March | Purpose: Provide parents with a centralised hub for all onboarding and support resources. Features: Searchable Knowledge Base: Allow users to search for answers across general FAQs and billing help. General FAQ Content: Include topics such as bookings, cancellations, session updates, and child support services. Clear Navigation: Organise FAQs into categories like “Getting Started,” “Bookings,” and “Payments.” CTA for Additional Support: Include a clear link to contact the dedicated support team for unresolved issues (e.g., “Still need help? Contact our team here.”). Technical Requirements Search and Routing: Implement a robust search function for the knowledge base and billing FAQs. Ensure persona routing logic is clear and intuitive. CMS Integration: Enable the business team to update FAQs and persona-based pages as needed. Responsive Design: Ensure all features are optimised for mobile and desktop use. Analytics and Reporting: Track user interactions (e.g., search queries, FAQ views, and contact clicks) to identify common pain points.
PP new customer section | 3 |  | create high-level design concept | review existing designs | prepare for testing / iterate | validate designs w customers | detailed design | review existing designs | prepare for testing / iterate | validate designs w customers
notifications
preference center |  | Develop a “My Settings” section within the Parent Portal to allow users to adjust notifications and manage billing preferences. The section should include the following functionality: Communications Preferences: opt in/out of emails and sms (as part of Communication Preferences): Notification Preferences: Enable users to toggle on/off specific types of notifications (e.g., booking reminders, payment alerts, service updates). Provide clear categories for notifications (e.g., General Updates, Billing Alerts, Child Activity Highlights). Include real-time save confirmation after changes. Billing Preferences: Allow users to update payment methods (e.g., switching between bank transfer and credit card). Include an option to adjust payment dates within allowed flexibility. Display the current billing setup and provide actionable links for changes (e.g., “Update Card Details”). Security and Accessibility: Include secure authentication to protect sensitive billing information - 2FA/MFA in billing interactions Ensure the section is responsive and user-friendly on both desktop and mobile devices. Integration and Updates: Connect seamlessly with the backend payment and notification systems to ensure changes are reflected in real time. Log user changes for troubleshooting and compliance purposes. Banner or Help Option: Add a help section or FAQ link for users who need guidance on notification or billing adjustments. | create high-level design concept | prepare for testing / iterate | validate designs w customers
Notifications hierarchy and critical detailed design concepts | 1 |  | create high-level design concept | detailed design | validate designs w customers
Maguire notifications | 1 | Upcoming Payment Reminders: Notify parents about upcoming due dates for payments. | detailed design
Maguire notifications | 1 | Missed Payment Follow-Ups: Escalating reminders for overdue payments, requiring acknowledgment after a certain period. | detailed design
Maguire notifications | 1 | Bounced Payment Alerts: Immediate notification of failed payment attempts, requiring acknowledgment. | detailed design
Maguire notifications | 1 | First Payment Reminder (New Customers): Notify new customers about their first payment due. | detailed design
Maguire notifications | 2 | Billing Adjustments: Notify parents about new payment options or changes to billing processes. | detailed design
Community Notifications | 2 | Event Invitations: Inform parents about upcoming events or activities at the service. | detailed design
Community Notifications | 1 | Service Closures (Planned or Emergency): Notify parents of planned closures or real-time updates for emergencies. | detailed design
Community Notifications | 1 | Weekly Program Updates: Share details of upcoming programs and activities. | detailed design
Community Notifications | 1 | Staffing Updates: Changes to team or team arrangements | detailed design
Admin Notifications | 2 | Service Registration Confirmation: Confirm successful registration for a service. | detailed design
Admin Notifications | 1 | Booking Change Notifications: Notify parents of changes to their bookings, requiring acknowledgment for significant changes. | detailed design
Admin Notifications | 2 | Policy Updates: Notify parents about policy changes, requiring acknowledgment to continue using the portal. | detailed design
Feedback & Survey Notifications | 2 | Post-Service Feedback Requests: Request feedback on the parent or child experience after a service. | detailed design
Feedback & Survey Notifications | 2 | NPS Parent Survey: Invite parents to participate in an annual or periodic survey to measure satisfaction. | detailed design
Feedback & Survey Notifications | 1 | Service Feedback Changes: Inform parents about adjustments or improvements made based on their feedback. | detailed design
Feedback & Survey Notifications | 1 | Feedback Progression in the Chain: Notify parents about how their feedback is being actioned within the system or service. | detailed design
Emergency Notifications | 1 | Unplanned Service Closures: Notify parents of emergency closures in real time. | detailed design
Attendance & Booking Notifications | 1 | Child-Specific Emergencies: Immediate notification about issues specific to a child, requiring acknowledgment. | detailed design
Attendance & Booking Notifications | 1 | Upcoming Bookings: Remind parents of their upcoming bookings. | detailed design
Attendance & Booking Notifications | 1 | Booking Confirmations: Confirm successful bookings in real time. | detailed design
Attendance & Booking Notifications | 1 | Waitlist Notifications: Notify parents when a spot becomes available for a waitlisted booking. | detailed design
Preferences & Account Notifications | 1 | Sign-in/Out Notifications: Notify parents when a child signs in or out of the service. | detailed design
General Announcements | 2 | Notification Preferences Update: Notify parents about updates to notification options. | detailed design
General Announcements | 1 | Password Changes: Immediate notification of password updates, requiring acknowledgment. | detailed design
General Announcements | 2 | Unusual Login Alerts: Notify parents of unusual login activity, requiring acknowledgment. | detailed design
Rewards, Gamification, and Loyalty Notifications | 2 | New Programs or Services: Notify parents about newly introduced programs or services. | detailed design
Rewards, Gamification, and Loyalty Notifications | 2 | Seasonal/Holiday Updates: Share updates about special holiday programs or activities. | detailed design
Security & Privacy Notifications | 3 | Loyalty Points Earned: Notify parents about loyalty points accumulated for engagement or bookings. | detailed design
Security & Privacy Notifications | 3 | Milestone Rewards: Notify parents of rewards earned for specific milestones, such as attendance. | detailed design
Engagement Notifications for Families | 1 | Daily Highlights: Provide summaries of a child’s daily activities or achievements. | detailed design
Engagement Notifications for Families | 1 | Activity Reminders: Remind parents of special upcoming activities for their child. | detailed design
Compliance Notifications | 1 | Health & Safety Forms: Remind parents to submit required forms, requiring acknowledgment upon completion. | detailed design
2025-01-13
2025-01-14
2025-01-15
2025-01-16
2025-01-17
2025-01-18
2025-01-19
2025-01-20
2025-01-21
2025-01-22 |  | project approval
2025-01-23
2025-01-24
2025-01-25
2025-01-26
2025-01-27
2025-01-28
2025-01-29
2025-01-30
2025-01-31
2025-02-01
2025-02-02
2025-02-03
2025-02-04
2025-02-05
2025-02-06
2025-02-07
2025-02-08
2025-02-09
2025-02-10
2025-02-11 | [7 empty] | x
2025-02-12
2025-02-13
2025-02-14
2025-02-15
2025-02-16
2025-02-17
2025-02-18
2025-02-19
2025-02-20
2025-02-21
2025-02-22
2025-02-23
2025-02-24
2025-02-25
2025-02-26
2025-02-27
2025-02-28
2025-03-01
2025-03-02
2025-03-03
2025-03-04
2025-03-05
2025-03-06
2025-03-07
2025-03-08
2025-03-09
2025-03-10
2025-03-11
2025-03-12
2025-03-13
2025-03-14
2025-03-15
2025-03-16
2025-03-17
2025-03-18
2025-03-19
2025-03-20
2025-03-21
2025-03-22
2025-03-23
2025-03-24
2025-03-25
2025-03-26
2025-03-27
2025-03-28
2025-03-29
2025-03-30
2025-03-31
2025-04-01
2025-04-02
2025-04-03
2025-04-04
2025-04-05
2025-04-06
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Lena Belin can we please also include a contact us form with drop downs so that customers can easily select what their query relates to. Billing, Booking, CCS, Other (we can get CSC input for which categories would be best) Reply: @Robyn Simper agree - I have this under the billing section (line 22 onwards) but in my mind this should be everywhere including at the higher hierarchy level (Billing FAQs would be part of this general help section). Do you think we need should consolidate and move the whole support experience up here in one block instead?
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Lena Belin can we please also include a contact us form with drop downs so that customers can easily select what their query relates to. Billing, Booking, CCS, Other (we can get CSC input for which categories would be best) Reply: @Robyn Simper agree - I have this under the billing section (line 22 onwards) but in my mind this should be everywhere including at the higher hierarchy level (Billing FAQs would be part of this general help section). Do you think we need should consolidate and move the whole support experience up here in one block instead?
Note on C13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Lena Belin this preference centre should also include ability to opt in/out of emails and sms Reply: Also add 2FA/MFA when updating payment details Reply: Done, thank you @Robyn Simper

## Notifications
• Upcoming Payment Reminders: Email or optional push notification, not binding.
• Missed Payment Follow-Ups: Escalating push notifications, binding (must click after escalation).
• Bounced Payment Alerts: Immediate push notification, binding (must click and view).
• First Payment Reminder (New Customers): Email notification only, not binding.
• Event Invitations: Optional push notification, not binding.
• Service Closures (Planned or Emergency): Real-time push notification for emergency closures; optional for planned, not binding.
• Weekly Program Updates: Optional push notification, not binding.
• Service Registration Confirmation: Email notification only, not binding.
• Booking Change Notifications: Real-time push notification, binding (must click to acknowledge changes).
• Policy Updates: Email notification only, binding (must acknowledge to continue portal use).
• Post-Service Feedback Requests: Optional push notification, not binding.
• NPS Parent Survey: Optional push notification, not binding.
• Unplanned Service Closures: Real-time push notification, not binding.
• Child-Specific Emergencies: Real-time push notification, binding (must click and view).
• Upcoming Bookings: Optional push notification, not binding.
• Booking Confirmations: Real-time push notification, not binding.
• Waitlist Notifications: Real-time push notification, not binding.
• Sign-in/Out Notifications: Optional push notification, not binding.
• Notification Preferences Update: Email or optional push notification, not binding.
• New Programs or Services: Optional push notification, not binding.
• Seasonal/Holiday Updates: Optional push notification, not binding.
• Service Feedback Changes, informing parents about adjustments or improvements made to services based on their feedback: Optional push notification, not binding.
• Loyalty Points Earned: Optional push notification, not binding.
• Milestone Rewards: Optional Email or push notification, not binding.
• Password Changes: Immediate push notification, binding (must click and acknowledge).
• Unusual Login Alerts: Immediate push notification, binding (must click and view).
• Daily Highlights: Optional push notification, not binding.
• Activity Reminders: Optional push notification, not binding.
• Feedback provided and progression of feedback in the chain Notifications: Optional push notification, not binding.
• Health & Safety Forms: Email or optional push notification, binding (must submit forms).
• Policy Updates: Email notification only, binding (must acknowledge to proceed).